## Campaign action plan
Phase | Activity | Description / outputs | Audience | Lead team | Supporting teams | Channel / format | Key dependencies | Start date | End date | Status | Notes / learning
Insight & planning | Customer insight gathering | Surveys, feedback, frontline insight, social listening | Customers | Customer insight | Comms, Customer service | Survey / workshops | Data protection sign-off
Insight & planning | Internal insight gathering | Frontline staff feedback on common questions and myths | Colleagues | Comms | Lettings, Neighbourhoods | Workshops / interviews | Staff availability
Content creation | Web hub copy | Core campaign page explaining who gets our homes | Customers / stakeholders | Comms | Lettings, Policy | Website | Policy accuracy sign-off
Content creation | FAQ content | Plain-English answers to common questions | Customers | Comms | Lettings, Customer service | Website / PDF | Lettings input
Content creation | Social copy | Myth-busting posts and explainer threads | Customers / public | Comms | Customer service | Social media | Tone and moderation guidance
Content creation | Graphics | Infographics, tiles, diagrams | All | Comms | Design | Digital / print | Brand sign-off
Delivery | Post scheduling | Schedule campaign posts across platforms | Customers / public | Comms | — | Social scheduling tool | Final content sign-off
Delivery | In-person events | Let's Talk Facts sessions with residents | Customers | Community engagement | Lettings, ELT | Community venues | Venue booking and staffing
Delivery | Internal briefings | Brief staff on messages and tone | Colleagues | Comms | ELT | Meetings / intranet | Leadership availability
Evaluation | Campaign monitoring | Track engagement, questions, sentiment | All | Comms | Customer insight | Dashboards | Data access
Evaluation | Post-campaign review | What worked, what to improve, learning log | Internal | Comms | All teams | Review session | Data collated